## Action Items
Annex M
PEDAL PLAY MOBILE RODEO PLANNING DOC - 2017
ACTION ITEMS | START DATE | FINISH DATE | PRIMARY POC | SECONDARY POCs | COMMENTS/NOTES
Confirm purpose and target audience
Set event date; month, day and time (identify any potential neighbourhood event conflicts)
Develop/confirm route, and participating schools/community centres/parks etc.
Develop route cue sheet (detailed route instructions indicating kilometers)
Establish main/core planning committee
Confirm availability of participating schools (and identify possibility of potential event conflicts - esp in parking areas)
Book facilities including access to washroom facilities
Identify and contact support groups and their contribution (Bike Mechanics, Public Health, OPP, Boy Scouts, etc)
Identify and book suitable First Aid Service (ie Ski Patrol or St. John’s Ambulance )
Prepare/update all correspondence (letters to schools and partners, PR documentation etc)
Prepare/update and submit documentation (safety plan) for event insurance
Prepare, seek approval of operating budget and determine process for receiving funds and making payments
Create event sponsorship program and seek organizations/businesses to sponsor (food, prizes, volunteer tee-shirts, activity station sponsorship etc )
Develop volunteer recruitment parameters
Determine and initiate all means/methodologies of recruiting suitable volunteers
Determine/identify all means/methodologies of promotion
Update and translate poster and passport
Develop simplified registration process (including waiver), electronic and paper
Obtaining school board approval to send information to students and parents;
Develop/update station activities, learning points, and write protocols
Determine event logistics; activities and their required location
Determine location of support groups and confirm their special equipment requirements (electricity, tables etc)
Deveop an overall site plan
Develop a site plan specifically for each school (indicating activity location)
Recruit crossing guards
Determine/allocate volunteer assignments and prepare event contact sheet (include cell numbers and station assignments)
Set volunteer training dates
Prepare volunteer training material
Book volunteer training room(s)
Print passports, posters, PR material
Develop and provide Event Evaluation process for planning committee, participants, and volunteers
Purchase volunteer t-shirts
Order/borrow volunteer safety vests
Identify and order event support material (chalk, route markings, stickers, etc)
Develop and print activity support posters (HTA and special diagrams)
Develop and print area identifiers/signs ( registration, finish, and other areas)
Obtain/rent/borrow special equipment (pylons, barriers, safety vests)
Order volunteer refreshments for registration
Provide 'lessons learned' to Stakeholders
Host Volunteer Appreciation event - or send "thank yous"
Develop generic 'How To' handbook/tool box for other communities/users

## Team Contacts
Core Planning Committee
Position | Name | E-mail | Phone | Comments
Project manager(s) | Julie |  | 613 869-1659
| Monna | monnaleigh@hotmail.com | 613 599-1258 | out of town; Dec - End Apr
Safety and Education POC | Monna | monnaleigh@hotmail.com | 613 599-1258 | out of town; Dec - End Apr
Promotion and social media POC
Sponsorship/fundraising POC
Volunteer recruitment POC |  |  |  | must ensure clarity of requirement, and assurance of competencies
Volunteer organizer/allocator/trainer | Monna | monnaleigh@hotmail.com | 613 599-1258 | out of town; Dec - End Apr

## Docs
Documentation:
Correspondence to schools, parents and Community Centres (requests and thank yous);
Route cue sheet;
Station activity and learning point protocols;
Activity support posters (HTA and special diagrams); and
Safety plan (for event insurance);
Correspondence for Sponsorship (requests and thank yous);
Correspondence for Support Groups (requests and thank yous);
Correspondence for promotional: Passports, posters, pamphlets etc
Press releases
Certificates of Appreciation for volunteers and committee members.